# AI Student Routine Manager

## Complete JIRA Project Setup Guide

For Teammates - Project Management Course (Spring 2025-2026)

## Introduction

This document is a readable version of the JIRA guide content from your docx script.

Use it as the source-of-truth checklist to create and organize the project in JIRA.

Project overview:

- Name: AI Student Routine Manager

- Type: Full-stack web application

- Purpose: Students input class schedules and habits; AI generates realistic gap-free daily routines.

- Stack: Next.js, Tailwind, Supabase, Claude (primary), Gemini/OpenRouter/Groq fallbacks, Vercel, Telegram Bot API

- Constraint: Free tiers only

### What to write in your report

- Write 1 short paragraph introducing the project goal and who the users are.

- Explain the problem solved: students struggle to plan realistic daily schedules.

- Explain the solution: AI-assisted routine generation plus progress tracking and reminders.

- Mention constraints: free-tier services, semester deadline, team-based development.

### What to add in JIRA

- Project name and key exactly: AI Student Routine Manager (ASRM).

- Project description (copy this):

- "A full-stack web app that builds realistic daily student routines from class schedules and habits, with AI generation, dashboard tracking, and Telegram reminders."

## Section 1 - Project Type: Scrum

Select Scrum (not Kanban) because the project has:

- A fixed semester deadline (14 weeks)

- Clear scope and defined backlog

- Time-boxed delivery in sprints

- Formal roles and review cycles

Scrum points to mention in report:

- Fixed-length sprints

- Prioritized product backlog

- Sprint planning, review, retrospective

- Acceptance criteria per story

- Story point estimation (Fibonacci)

### What to write in your report

- Add a heading: Why we selected Scrum.

- Write 5-7 sentences covering:

- Fixed 14-week deadline

- Defined scope from start

- Work split into 4 sprints

- Roles and ceremonies

- Need to inspect/adapt each sprint

- Add one comparison sentence: Kanban is less suitable for fixed-semester scope/deadline.

### What to add in JIRA

- During project creation, choose Scrum template.

- Confirm Team-managed project.

- Set sprint cadence to 2-3 weeks.

## Section 2 - JIRA Setup Steps

- Create JIRA account at jira.atlassian.com

- Create project:

- Template: Scrum

- Name: AI Student Routine Manager

- Key: ASRM

- Type: Team-managed

- Assign roles:

- Product Owner

- Scrum Master

- Developers

- Create sprints:

- Sprint 1: Foundation (Weeks 1-3)

- Sprint 2: AI Core (Weeks 4-7)

- Sprint 3: Dashboard & Alerts (Weeks 8-11)

- Sprint 4: Deployment & Polish (Weeks 12-14)

### What to write in your report

- Add subsection: JIRA Project Configuration.

- Include:

- Account creation summary

- Project template + key choice

- Team roles and responsibilities

- Sprint names and date ranges

- Add 1 screenshot reference for project settings and 1 for backlog with sprints.

### What to add in JIRA

- Add members and map:

- Product Owner (backlog prioritization)

- Scrum Master (facilitation/blockers)

- Developers (implementation)

- Create all 4 sprints in backlog before creating issues.

- Keep sprint names exactly as listed above.

## Section 3 - Epics

Create these 6 epics:

- ASRM-E1 User Authentication & Account Management

- ASRM-E2 9-Screen Onboarding Questionnaire

- ASRM-E3 AI Schedule Generation Engine

- ASRM-E4 Interactive Dashboard & Timeline

- ASRM-E5 Telegram Notification System

- ASRM-E6 Deployment, Performance & Production Setup

### What to write in your report

- Add subsection: Epic Breakdown.

- For each epic, write:

- 1 sentence objective

- Why it is important

- Which sprint(s) mainly cover it

- Mention that epics are containers and stories/tasks are planned into sprints.

### What to add in JIRA

- Create 6 epic issues with IDs/titles above.

- In each epic description add:

- Goal

- Scope boundaries (what is included/excluded)

- Related sprint window

- Optional: apply distinct epic colors for readability.

## Section 4 - Stories (ASRM-1 to ASRM-20)

Story groups:

- Authentication: ASRM-1, ASRM-2, ASRM-3

- Onboarding: ASRM-4, ASRM-5, ASRM-6, ASRM-7

- AI Engine: ASRM-8, ASRM-9, ASRM-10, ASRM-11

- Dashboard: ASRM-12, ASRM-13, ASRM-14, ASRM-15

- Telegram: ASRM-16, ASRM-17

- Deployment: ASRM-18, ASRM-19, ASRM-20

Each story should include:

- Summary

- User story statement

- Acceptance criteria

- Priority

- Story points

- Epic link

- Sprint

### What to write in your report

- Add subsection: User Stories and Value Delivery.

- Explain story format:

- "As a [user], I want [action], so that [benefit]."

- For each epic, summarize 2-4 key stories and expected user value.

- Add note that acceptance criteria define "done".

### What to add in JIRA

- For each story, complete these fields:

- Summary

- Description (full user story + acceptance criteria)

- Priority

- Story points

- Epic link

- Sprint

- Keep naming/numbering exactly ASRM-1 to ASRM-20.

- Use acceptance criteria checklist style to make validation easier.

### Copy-ready story description template

- User Story:

- "As a [role], I want [feature], so that [value]."

- Acceptance Criteria:

- [ ] Criterion 1

- [ ] Criterion 2

- [ ] Criterion 3

- Notes:

- Dependencies:

- Edge cases:

## Section 5 - Tasks

Tasks are linked technical actions under stories.

Examples in your original script include detailed task sets under:

- ASRM-1 (Sign-Up)

- ASRM-2 (Sign-In)

- ASRM-3 (Route Protection)

- ASRM-8 (Pre-computation)

- ASRM-9 (AI Fallback Chain)

- ASRM-12 (Timeline UI)

- ASRM-17 (Telegram Alerts)

### What to write in your report

- Add subsection: Task Decomposition.

- Explain that tasks are technical implementation units under stories.

- Mention each task has owner, points, and status.

- Give one example of decomposition (for example ASRM-8 precompute tasks).

### What to add in JIRA

- For each story, add child tasks using clear action verbs:

- Configure / Implement / Validate / Test / Refactor

- Fill task fields:

- Summary

- Parent story link

- Assignee

- Story points

- Status

- Keep task IDs/names consistent with your guide tables.

### Copy-ready task template

- Task Summary: "[Verb] [component/feature]"

- Description:

- Technical objective:

- Steps:

- Definition of done:

## Section 6 - Bugs

Create and document these bugs:

- ASRM-B1: Gemini model deprecation issue

- ASRM-B2: Dashboard rendered unstyled

- ASRM-B3: Runtime Error: [object Event]

- ASRM-B4: Illogical AI schedule generation

- ASRM-B5: Windows npm execution policy issue

- ASRM-B6: Onboarding data shape mismatch

Each bug should include:

- Steps to reproduce

- Expected result

- Actual result

- Root cause

- Fix applied

- Files changed

- Priority, points, status, sprint

### What to write in your report

- Add subsection: Defect Tracking and Resolution.

- Explain bug lifecycle:

- Discovery -> Reproduction -> Root cause -> Fix -> Verification

- Mention that each bug ticket includes evidence and fix documentation.

- Briefly highlight high-impact bugs (B1, B2, B4) and lessons learned.

### What to add in JIRA

- Create bug tickets ASRM-B1 to ASRM-B6.

- Use structured description blocks:

- Steps to reproduce

- Expected result

- Actual result

- Root cause

- Fix applied

- Files changed

- Set priority, points, sprint, and final status.

### Copy-ready bug template

- Steps to reproduce:

1.

2.

3.

- Expected result:

- Actual result:

- Root cause:

- Fix applied:

- Files changed:

- Verification result:

## Section 7 - Sprint Summary

- Sprint 1: 21 points

- Sprint 2: 39 points

- Sprint 3: 26 points

- Sprint 4: 10 points

- Grand total: 96 points

### What to write in your report

- Add subsection: Sprint Plan and Workload Distribution.

- Include a short paragraph per sprint:

- Main focus

- Key stories/bugs

- Total points

- Add a final sentence interpreting workload balance across the semester.

### What to add in JIRA

- Confirm each story/bug is assigned to the correct sprint.

- Ensure sprint point totals match this section.

- Start Sprint 1 with correct date range; keep later sprints planned.

## Section 8 - Teammate Checklist

- Setup account and project

- Create 4 sprints

- Create 6 epics

- Create all stories

- Create all tasks

- Create all bugs

- Start Sprint 1

- Capture required screenshots for report appendix

### What to write in your report

- Add subsection: Execution Checklist Followed by Team.

- State that all setup and issue creation steps were completed in sequence.

- Add screenshot index list (caption + what each screenshot proves).

### What to add in JIRA / Evidence folder

- Capture and store screenshots for:

- Project home + members

- Roadmap (all epics)

- Backlog (all sprints)

- Story details (criteria, points, epic link)

- Task list under a story

- Bug details

- Active sprint board

## Section 9 - Glossary

Include definitions for:

- Epic

- Story

- Task

- Bug

- Subtask

- Sprint

- Backlog

- Story Points

- Acceptance Criteria

- Product Owner

- Scrum Master

- Sprint Planning

- Sprint Review

- Burndown Chart

- Epic Link

### What to write in your report

- Put this as an appendix/subsection named Glossary of Agile/JIRA Terms.

- Keep each definition to 1-2 lines max.

- Use consistent plain language (avoid tool jargon overload).

### What to add in JIRA context

- No new issues needed here.

- Ensure terms used in tickets match glossary wording (Epic, Story, Task, Bug, Story Points, Acceptance Criteria).

## Optional: Generate .docx from your original script

You already have the full docx builder code. To generate a Word file directly in this repo:

- Save your JS as scripts/generate-jira-guide.js

- Ensure dependency is installed:

- npm install docx

- Update output path in script to:

- ./JIRA_Complete_Guide.docx

- Run:

- node scripts/generate-jira-guide.js

## Final submission pack (recommended)

Include these files in your final handoff:

- JIRA_Complete_Guide_READABLE.md (editable source)

- JIRA_Complete_Guide_READABLE.docx (report-ready)

- Screenshot folder:

- 01_project_setup.png

- 02_sprints_backlog.png

- 03_epics_roadmap.png

- 04_stories_backlog.png

- 05_tasks_under_story.png

- 06_bug_ticket.png

- 07_active_sprint_board.png

Optional additions for higher quality:

- Team role matrix (name -> role -> responsibility)

- Risk list (top 3 risks + mitigation)

- Definition of Done checklist used by team